HEE Maternity Programme Update
January 2021

Contents

Programme Overview	1

Covid-19	1

Midwifery Workforce	2

Maternity Support Workforce (MSW)	4

Maternity Workforce Development	5

Neonatal	6

Other Updates	6

# Programme Overview

The Maternity Transformation Programme (MTP) led by NHS England is delivering the Better Births vision of improving maternity care in England, through ten workstreams. HEE is leading on Workstream 5 (transforming the workforce) to help shape the future maternity workforce so it can implement the workforce requirements outlined in Better Births and support new models of care.

HEE is also supporting workstream 1 (transformation), workstream 2 (promoting good practice for safer care), workstream 9 (prevention) and workstream 10 (neonatal) led by NHSE/I. This is to help deliver the government’s ambition to reduce the rate of stillbirths, neonatal and maternal deaths and intrapartum brain injuries in babies in England by 20% by 2020 and 50% by 2025. Please see our governance chart below:

Joint HEE/RCOG Medical Workforce Group

NHSE/I Maternity Transformation Programme (MTP) Board

Midwifery Workforce Steering Group (MiWSG)

Maternity Support Worker Oversight Group (MSWOG)

HEE Board

HEE Department of Education (DEQ) Senior Leadership Team

Maternity Programme Oversight Group (MPOG)

Maternity Programme Assurance Committee (MPAC)

HEE Regional Maternity Leads

Covid-19

- HEE Online Resources

HEE e-Learning for Healthcare (e-LfH) has added additional learning paths for nurses, midwives & AHPs to an e-learning programme designed to help the workforce during Covid-19. There is also a specific programme entitled ‘Resources for Nurses, Midwives and AHPs Returning to work, being Redeployed or Up-Skilled’ which may help during Covid-19.

Please see our updated catalogue by clicking here.

HEE has also launched a bespoke webpage dedicated to support midwives during Covid-19. This includes up-to-date national guidelines, case studies and other resources and can be accessed here.

# Midwifery Workforce

- Expansion of Midwifery Training Places

As per the government mandate and the system wide Maternity Workforce Transformation Strategy, HEE is committed to increasing the number of midwifery training places by 25% over a 4-year period, to ensure future sustainability from 2022.

On the 2018/19 baseline of 2665 there is a commitment to have increased training places by 650 in 2019/20 and up to a further 1000 places per year for a period of three years after that.

HEE is pleased to announce it has achieved 95% of the mandated target of 650 additional training places by March 2020; numbers confirmed through the HEE Student Data Collection Tool (SDCT) show an increase of +615 for 2019/20. This is inclusive of undergraduates, spring cohorts, apprentices and postgraduate courses. HEE is now working towards the 2020/21 mandate of up to +1000.

Update:

HEE intends to be able to update on growth within 2020/21 so far through Autumn cohorts in February 2021. An update will be provided in the next briefing.

- Continuity of Carer (CoC) National Training Offer

The national Continuity of Carer training offer for 2019/20 was created by the HEE Maternity Programme in collaboration with NHSE/I and key stakeholders. Three partnering organisations were procured to deliver a training package across HEE’s seven regions. To deliver this training, HEE has commissioned the following providers:

- Improving Performance in Practice (iPiP); The University of the West of England (WE) & the University of Plymouth; and Birmingham City University (BCU).

Alongside this face-to-face training, each provider is to provide Masterclasses aimed at local leaders and other senior managers involved with the delivery of maternity services.

Update:

Due to Covid-19 face to face training is currently paused due to social restriction guidelines. Working with our commissioned training providers, HEE is pleased to update that virtual training is now being delivered across England for both the midwifery and masterclass sessions. Training sessions in some regions have commenced and in other regions discussions on priority areas to commence training are taking place with Local Maternity Systems (LMS).  For further information on training in your area please contact maternityprogramme@hee.nhs.uk or your Regional HEE Maternity Lead.

- Continuity of Carer (CoC) E-Learning

HEE, in partnership with Improving Practice in Performance (iPiP), has launched a new e-learning session to the Midwifery Continuity of Carer (McoC) programme.

This programme provides participants with an overview of the underpinning policy changes which have informed both the development of Midwifery Continuity of Carer (MCoC) models and proposed changes of midwifery care in England.

This resource provides a base level of understanding of Midwifery Continuity of Carer, its policy drivers and evidence base for delivery. This session is a pre-requisite to be completed prior to attending the National Midwifery Continuity of Carer training workshops and masterclasses. However, this programme is also open to all who wish to learn more about maternity continuity of carer which may include midwives, maternity support workers, obstetricians, managers and commissioners.

For more information about the programme, including details of how to access, visit: https://www.e-lfh.org.uk/programmes/midwifery-continuity-of-carer/.

# New E-learning packages

Health Education England e-Learning for Healthcare has worked with Public Health England to create the Reintroduction of CO Testing e-learning resource. This course aims to refresh the knowledge and skills of midwives and health visitors in undertaking very brief advice and using a carbon monoxide (CO) monitor. (Dec 2020)

Health Education England e-Learning for Healthcare (HEE e-LfH) has worked with the Wellbeing of Women charity to update the Medical Problems in Pregnancy e-learning programme. The programme is primarily designed for internal medicine trainees but will also be of use to others in ACCS (Acute Care Common Stem), obstetrics and anaesthesia and allied health professionals. Six sessions within the module have been reviewed and updated to represent current knowledge and guidelines. More information and access details are available on the Medical Problems in Pregnancy programme page and the programme evaluation survey is now live and available within the updated sessions. (Jan 2021)

Health Education England e-Learning for Healthcare has worked with Public Health England to update the Newborn Hearing Screening Programme (NHSP). The newborn hearing screening test helps to identify babies who have permanent hearing loss as early as possible. This means that parents can get the advice and support they need as soon as possible after birth. (Dec 2020)

# Maternity Support Workforce (MSW)

- MSW Framework Implementation

The Maternity Support Worker Competency, Education and Career Development Framework, developed in partnership with the University of the West of England (UWE) was launched 14 February 2019.

As part of this development, there was extensive engagement with stakeholders, including a series of regional stakeholder engagement events which were held throughout October and November 2018.  Phase 3 of our MSW work, to map existing education programmes to the framework, is underway.

To support implementation of the framework the Maternity Support Worker Oversight Group (MSWOG) has created task & finish groups:

HEE has successfully commissioned the University of West England (UWE) to develop a curriculum to support the framework’s implementation.

- Pilot Sites

HEE is pleased to have worked with North West London (NWL) as a pilot site for implementation of the MSW Framework. In June 2020 a cost-benefit analysis was published and is available from here.

This work also aims to utilise the Senior Healthcare Support Worker Apprenticeship and other available resources to support MSW development. Work is on-going within a number of HEE regions to support this process further.

- Maternity Support Worker 2020/21 Funding Offer

The HEE Maternity & CYP Programme has secured a £1 million investment to support implementation of the MSW Framework.

This MSW Transformation Fund was launched in August 2020 and will help Local Maternity Systems (LMS) map their existing MSWs to the competencies within the framework.  In doing so, HEE is supporting the development of a competent MSW workforce which promotes safer care, safer staffing and working towards the vision outlined in Better Births: Improving outcomes of maternity services in England (2016).

43 out of 44 LMS have taken up the offer of support and are undertaking the scoping work outlined in the funding offer.  Further information on this offer can be found on our website here.

Update:

HEE is working with LMS to monitor progress and will receive a summary report from all LMSs by 31 March 2021.

# Maternity Workforce Development

- Obstetric Ultrasound Training Evaluation

In 2017/18 HEE facilitated training to upskill staff to be able to perform third-trimester ultrasound procedures following a Secretary of State directive for 200 additional staff to be trained. In total, HEE supported the training of 241 staff across the NHS. To evaluate this work and inform future work in this field, the Maternity Programme has procured a national partner.

Update:

The survey successfully launched in October 2020 and closed late November.  The final evaluation report and future workforce recommendations are due to be published in Q1 2021.

- Advanced Clinical Practice (ACP) in Midwifery

HEE has established a project to develop midwifery standards via a framework relating to advanced clinical practice (ACP) in midwifery. To undertake this the University of East Anglia (UEA) was commissioned to undertake a deep dive review of the current ACP Midwife, Specialist Midwife and Consultant Midwife workforce in England.

This piece of work also included a mapping of the competencies within the Nursing & Midwifery Council (NMC) Standards for Midwifery (both the pre- and post-2020 standards) against the national HEE Multi-professional framework for advanced clinical practice in England.

Update:

We are pleased to report we received a draft version of this report in December 2020, and it will be published in the coming months. The report contains 10 recommendations for the system and these are being review by the ACP in Midwifery steering group.

# Neonatal

- Neonatal Qualified in Speciality (QIS) Deep-Dive

As part of workstream 10, HEE is supporting the Neonatal Implementation Board (NIB) implement the recommendations of the Neonatal Critical Care Review (NCCR). As part of this HEE is planning to undertake a national review of Neonatal Qualified in Speciality (QIS) training in England.

HEE is pleased to have commissioned RSM UK to undertake this review which will

include a review of access to programmes, supply and demand for training programmes, quality and consistency of programmes, evaluation and accreditation of QIS programmes against the British Association of Perinatal Medicine (BAPM) core syllabus and recommendations for potential future training routes in 2020.

Update:

This work started in September 2020 and will be delivered by March 2021. RSM UK is currently undertaking surveys and interviews across the system, and a national workforce delivery group has been created to monitor progress.

# Other Updates

- Saving Babies Lives Care Bundle (SBLCB) v2 e-Learning

In conjunction with NHSE/I, Public Health England (PHE), the Royal College of Obstetricians & Gynaecologists (RCOG), the Royal College of Midwives (RCM) and the British Intrapartum Society (BIS), HEE has supported the development of an e-Learning programme to support implementation of the SBLCB v2. It can be accessed here. This covers the following five key areas:

- Very brief advice on smoking for pregnant woman;

- Detection and surveillance of fetal growth restriction;

- Reduced fetal movements;

- Effective continuous fetal monitoring during labour;

- Reducing preterm birth. The programme is aimed at midwives and obstetricians.

Return to Practice (RtP)

For information:

The NMC has advised that reapproval against the new Return to Practice (RtP) standards is for all professions, including midwives and associate nurses. Nurses, midwives and nursing associates seeking readmission to the NMC register, if they are unable to satisfy readmission requirements, must successfully complete an NMC approved return to practice programme (RtP) or pass an NMC test of competence.

The 2019 Standards set out the legal and entry requirements, the programme content, methods of assessment and information on the credits/award for return to practice programmes. The standards set out the specific requirements that apply to all approved return to practice education programmes. Please refer to the Standards for Return to Practice Programmes (May, 2019) Section 2, page 8.

Pre-2019 RTP standards apply to courses already approved, the NMC are now approving new RtP programmes with full implementation by the end of August 2021.

Please note the NMC has extended the transition period for commencing pre-registration midwifery programmes to September 2022.

- Regional Maternity Leads

1

The Maternity Programme is delighted to see that HEE has appointed 7 maternity leads to support regional delivery of the maternity workstreams. These are as follows:

| Locality​ | Name​ |
| --- | --- |
| North East & Yorkshire ​ | Lesley Young (1) |
| North West ​ | Catherine Simm (2) |
| Midlands ​ | Amanda Battey (3)​ |
| East of England ​ | Gareth George (4)​ |
| London ​ | Caroline Ward (5) |
| South East ​ | John Clark and Agnes Hibbert (6) |
| South West ​ | Christine Doncom (7)​ |

- Midwifery Apprenticeship Standard Approved for Delivery

The apprenticeship standard for Midwives (NMC 2019) has been approved for delivery by the Institute for Apprenticeships & Technical Education.

Further information can be found on the Skills for Health webpage: https://haso.skillsforhealth.org.uk/news/midwife-nmc-2019-approved-for-delivery/

# The Learning Hub – suite of resources for midwives available to access

The Learning Hub is a digital platform that provides easy access to a wide range of education and training resources for the health and care workforce. Organisations and users can contribute and share resources for those in health and care to access.

Colleagues across health and care have been uploading resources and there are now 850 resources available to access and share with colleagues. The resources cover a variety of subjects including role specific content, mental health, COVID-19 resources (including self-swabbing) and how technology is being used to support simulation-based education and remote teaching during the pandemic.

Existing contributions of content to the Learning Hub include a suite of resources for hospital and community-based midwives from the West Midlands Neonatal Operational Delivery Network:

Managing respiratory tract secretions in self-ventilating babies

Community midwives poster

Keeping babies warm

Use of donor breast milk

Next briefing: March 2021

Maternity Programme
January 2021